## Gantt Chart
Enterprise Pro Team 9
Tasks | Start Date | Working days Needed | Completion | Adjusted Length | Assigned to
Frontend UI implementations | 2025-03-12 | 12 | 2025-03-28 | 16 | Huzaifa & Hanzala
Database setup | 2025-03-03 | 7 | 2025-03-12 | 9 | Sarim, Humaid & Geordy
API development | 2025-03-07 | 5 | 2025-03-14 | 7 | Geordy & Ali Hamza
Data visualization | 2025-03-12 | 7 | 2025-03-21 | 9 | Muhammad Ejaz & Huzaifa
Authentication and security | 2025-03-17 | 8 | 2025-03-27 | 10 | Sarim, Huzaifa & Ali Hamza
Testing and deployment | 2025-04-02 | 3 | 2025-04-07 | 5 | Entrie team
Flagging System | 2025-03-10 | 3 | 2025-03-13 | 3 | Humaid & Muhammad Ejaz
Documentation & Charts | 2025-02-24 | 30 | 2025-04-07 | 42 | Hanzala, Geordy & Humaid
Formulas:
Completion = WORKDAY([Start Date],[Working days Needed])